## Data
ASSOCIATED USER STORY | TASK | ESTIMATED TASK TIME | DATE COMPLETED
1 | Design wireframe for the application | 6 | 2016-04-11
1 | Setup iOS development environment | 8 | 2016-04-11
24 | Design page layout | 6 | 2016-04-11
24 | Generate wireframe for page layout | 2 | 2016-04-11
25 | Write source code for off-white background | 0.25 | 2016-04-12
25 | Write unit tests for off-white background | 0.25 | 2016-04-12
24 | Write source code for page layout | 8 | 2016-04-13
24 | Review source code for page layout | 1 | 2016-04-13
24 | Write acceptance criteria for page layout | 0.5 | 2016-04-13
24 | Write acceptance tests for page layout | 0.5 | 2016-04-13
25 | Review source code for off-white background | 0.25 | 2016-04-13
25 | Write acceptance criteria for off-white background | 0.25 | 2016-04-13
25 | Write acceptance tests for off-white background | 0.25 | 2016-04-13
26 | Write acceptance criteria for solo reading | 0.5 | 2016-04-13
26 | Write acceptance tests for solo reading | 0.5 | 2016-04-13
28 | Write source code for pictures in content | 4 | 2016-04-13
28 | Write unit tests for pictures in content | 1 | 2016-04-13
32 | Write source code for connecting with remote user | 16 | 2016-04-13
32 | Review source code for connecting with remote user | 2 | 2016-04-13
32 | Write acceptance criteria for connecting with remote user | 0.5 | 2016-04-13
32 | Write acceptance tests for connecting with remote user | 0.5 | 2016-04-13
33 | Write acceptance criteria for connecting with audio | 0.5 | 2016-04-13
33 | Write acceptance tests for connecting with audio | 0.5 | 2016-04-13
24 | Execute acceptance tests for page layout | 1 | 2016-04-14
25 | Execute acceptance tests for off-white background | 0.25 | 2016-04-14
26 | Write source code for solo reading | 3 | 2016-04-14
26 | Review source code for solo reading | 1 | 2016-04-14
26 | Write unit tests for solo reading | 1 | 2016-04-14
27 | Write source code for portrait and landscape modes | 6 | 2016-04-14
27 | Review source code for portrait and landscape modes | 0.5 | 2016-04-14
27 | Write unit tests for portrait and landscape modes | 1 | 2016-04-14
27 | Write acceptance criteria for portrait and landscape modes | 0.5 | 2016-04-14
27 | Write acceptance tests for portrait and landscape modes | 0.5 | 2016-04-14
28 | Review source code for pictures in content | 1 | 2016-04-14
28 | Write acceptance criteria for pictures in content | 0.5 | 2016-04-14
28 | Write acceptance tests for pictures in content | 0.5 | 2016-04-14
28 | Execute acceptance tests for pictures in content | 0.5 | 2016-04-14
29 | Write source code for adjustable font sizes | 3 | 2016-04-14
29 | Review source code for adjustable font sizes | 1 | 2016-04-14
29 | Write unit tests for adjustable font sizes | 1 | 2016-04-14
29 | Write acceptance criteria for adjustable font sizes | 0.5 | 2016-04-14
29 | Write acceptance tests for adjustable font sizes | 0.5 | 2016-04-14
32 | Execute acceptance tests for connecting with remote user | 1 | 2016-04-14
33 | Write source code for connecting with audio | 16 | 2016-04-14
24 | Write internal documentation for page layout | 1 | 2016-04-15
26 | Execute acceptance tests for solo reading | 1 | 2016-04-15
26 | Write internal documentation for solo reading | 0.5 | 2016-04-15
26 | Write user manual for solo reading | 0.5 | 2016-04-15
27 | Execute acceptance tests for portrait and landscape modes | 0.25 | 2016-04-15
27 | Write internal documentation for portrait and landscape modes | 1 | 2016-04-15
28 | Write internal documentation for pictures in content | 1 | 2016-04-15
29 | Execute acceptance tests for adjustable font sizes | 0.5 | 2016-04-15
29 | Write internal documentation for adjustable font sizes | 1 | 2016-04-15
29 | Write user manual for adjustable font sizes | 1 | 2016-04-15
32 | Write unit tests for connecting with remote user | 2 | 2016-04-15
32 | Write internal documentation for connecting with remote user | 1 | 2016-04-15
32 | Write user manual for connecting with remote user | 1 | 2016-04-15
33 | Review source code for connecting with audio | 1 | 2016-04-15
33 | Write unit tests for connecting with audio | 2 | 2016-04-15
33 | Execute acceptance tests for connecting with audio | 0.5 | 2016-04-15
33 | Write internal documentation for connecting with audio | 1 | 2016-04-15
33 | Write user manual for connecting with audio | 1 | 2016-04-15
116.75
Day
|  |  |  | 2016-04-11 | 116.75
|  |  |  | 2016-04-12 | 94.75
|  |  |  | 2016-04-13 | 94.25
|  |  |  | 2016-04-14 | 57.5
|  |  |  | 2016-04-15 | 17.25
|  |  |  | 2016-04-16 | 0