## Sheet1
# | Risk | Risk Ranking | Likelihood | Impact | Indicators | Contingency/Action
1 | Difficulties implementing voice recognition | 2 | Medium | Medium | Actual task implementation time starts exceeding estimates. Developpers growing frustrated trying to implement this technology. | Evaluate feature thoroughly before developing. Start developing features with voice recognition early on in the project to understand if there will be problems and issues. Seek out internal and external resources who could help solve problems and provide technical guidance.
2 | Issues implementing the remote connection with users | 2 | Medium | Medium | Video and/or audio connection drops during initial testing in development. | Evaluate features thoroughly before developing. Possibly prioritize voice over video communication for initial release. Start implementing these features early on to determine if (or which) problems arise.
3 | Unable to implement both Android and iOS versions in first release | 3 | High | Medium | Estimates exceed team bandwith. Start seeing compatibility issues between the two operating systems. | Clarify with the CIO whether the initial release should be developed on both platforms. If so, discuss the option of adding an additional developer to the team.
4 | The CIO may change her mind about which features she wants | 2 | Medium | Low | The CIO seems unsure or starts to question what the team has already agreed to develop. Or she explicitly requests that the team to change/add/remove features. | Rely on Agile processes to manage new requests and changes. Requests cannot be added to the current sprint, however they can be added to the backlog and prioritized during the next sprint planning session.
5 | Team member gets sick | 2 | Medium | High | Sickness starts spreading in the company. | Ensure good team communication of everyone's status of current tasks and issues, especially during the daily standup meeting. Ensure that team members are technically capable of picking up another team members work if necessary (i.e. make sure no one team member is indispensible.
6 | Database has been buggy in the past and could present insurmountable problems during developement. | 3 | High | HIgh | The database team's communication indicates that they are working on a number of critical issues. Other teams dependent upon the database indicate that they are having difficulties. Team members start finding problems during development. | Communicate regularly with the database team to ensure they understand our dependencies and issues. Send a representative to the database team's standup meeting. Start developing features that require database access first in order to determine if there are issues and how severe they are.
7 | Government could issue quartine or containment measures for Coronavirus that could impact the ability of the team to work in the office | 3 | High | High | Restrictions are issued for nearby locales. Media discussions regarding imminent restrictions. | Put systems and procedures in place now so that the team will be able to work from home, i.e. set up Zoom and Slack accounts and communicate ids, etc.
8 | This is a novel application that no one has yet developed and kids may not like it | 2 | Low | High | Kids don't use the app or don't use certain features. Kids stop using the app after a few tries. | Interview both parents and children to understand what they would value in an app. Conduct user acceptance testing with children as early as possible.
9 | Conflict among team members or personality issues impacts project progress or results in a team member leaving | 2 | Medium | High | Tension and/or conflict during team meetings and daily interactions. Team member seems unhappy or stressed. | PM should casually monitor team interactions and ensure that team members feel comfortable raising concerns and issues early on.
10 | Uncertainty as to how often reading comprehension tests should be given. | 1 | Low | Low | Customer feedback that test is too frequent or less frequent than they'd like | Montitor feedback from user testing