## Sheet1
US ID# | USER STORY | TASKS | HOUR ESTIMATE | ASSIGNED TO
1 | As a reader, I want the product to be mobile, so that I can use it anywhere | Design wireframe for the application | 6 | Team (2 hours each) | Very complete plan with good task breakdown.
|  | Setup iOS development environment | 8 | Kat
24 | As a reader, I want the view of a page to look close to the fidelity of a page in an actual book, so that it’s full story impact is maintained regardless of the medium | Design page layout | 6 | Team (2 hours each)
|  | Generate wireframe for page layout | 2 | You
|  | Write source code for page layout | 8 | Alexa
|  | Review source code for page layout | 1 | Kat | The team discussed peer programming in the task breakdown meeting, but the iteration plan does not reflect this. Instead each task that requires programming has only one programmer assigned to its associated "write source code" task and there is also a code eview task as well. This makes it look as if peer programming is not occurring. Unless the team has scrapped peer programming, the plan should be updated to assign multiple developers to a code task and the associated code review tasks should be eliminated.
|  | Write acceptance criteria for page layout | 0.5 | Kat
|  | Write acceptance tests for page layout | 0.5 | Kat
|  | Execute acceptance tests for page layout | 1 | You
|  | Write internal documentation for page layout | 1 | Alexa
25 | As a reader, I want the background of books to be off-white (as opposed to bright-white), so that I don't strain my eyes when I'm reading | Write source code for off-white backgrounds | 0.25 | Alexa | It is unusual to have estimates that are shorter that one hour, yet the plan has several especially in US #25. Perhaps these tasks can be combined into a larger one?
|  | Review source code for off-white backgrounds | 0.25 | Kat
|  | Write unit tests for off-white backgrounds | 0.25 | Alexa
|  | Write acceptance criteria for off-white backgrounds | 0.25 | Kat
|  | Write acceptance tests for off-white backgrounds | 0.25 | Kat
|  | Execute acceptance tests for off-white backgrounds | 0.25 | You
26 | As a reader, I want to be able to read material without a partner, so that I can read and practice at my own pace | Write source code for solo reading | 0.5 | Alexa
|  | Review source code for solo reading | 0.5 | Kat
|  | Write unit tests for solo reading | 3 | Alexa | Curious as to why the estimate for writing the unit tests for solo reading is 6 times as long as writing the code. Perhaps the writing code task is underestimated or the estimate for writing the unit tests is an error?
|  | Write acceptance criteria for solo reading | 1 | Kat
|  | Write acceptance tests for solo reading | 1 | Kat
|  | Execute acceptance tests for solo reading | 1 | You
|  | Write internal documentation for solo reading | 0.5 | Alexa
|  | Write user manual for solo reading | 0.5 | Alexa
27 | As a reader, I want the application to work in both portrait and landscape orientation, so that I can choose the way I view material | Write source code for portrait and landscape modes | 6 | Kat
|  | Review source code for portrait and landscape modes | 0.5 | Alexa
|  | Write unit tests for portrait and landscape modes | 1 | Kat
|  | Write acceptance criteria for portrait and landscape modes | 0.5 | Alexa
|  | Write acceptance tests for portrait and landscape modes | 0.5 | Alexa
|  | Execute acceptance tests for portrait and landscape modes | 0.25 | You
|  | Write internal documentation for portrait and landscape modes | 1 | Kat
28 | As a reader, I want any pictures associated with the content to appear with the text, so that they can supplement the reading material | Write source code for pictures in content | 4 | Kat
|  | Review source code for pictures in content | 1 | Alexa
|  | Write unit tests for pictures in content | 1 | Kat
|  | Write acceptance criteria for pictures in content | 0.5 | Alexa
|  | Write acceptance tests for pictures in content | 0.5 | Alexa
|  | Execute acceptance tests for pictures in content | 0.5 | You
|  | Write internal documentation for pictures in content | 1 | Kat
29 | As a reader, I want to be able to adjust font size, so that it is easier to read | Write source code for adjustable font sizes | 3 | Alexa
|  | Review source code for adjustable font sizes | 1 | Kat
|  | Write unit tests for adjustable font sizes | 1 | Alexa
|  | Write acceptance criteria for adjustable font sizes | 0.5 | Kat
|  | Write acceptance tests for adjustable font sizes | 0.5 | Kat
|  | Execute acceptance tests for adjustable font sizes | 0.5 | You
|  | Write internal documentation for adjustable font sizes | 1 | Alexa
|  | Write user manual for adjustable font sizes | 1 | Alexa
32 | As a reader, I want to be able to connect with a remote user, so that I know if I have access to someone with whom I can read | Write source code for connecting with remote user | 16 | Josh
|  | Review source code for connecting with remote user | 2 | Alexa
|  | Write unit tests for connecting with remote user | 0.5 | Josh
|  | Write acceptance criteria for connecting with remote user | 0.5 | Alexa
|  | Write acceptance tests for connecting with remote user | 1 | Alexa
|  | Execute acceptance tests for connecting with remote user | 2 | You
|  | Write internal documentation for connecting with remote user | 1 | Josh
|  | Write user manual for connecting with remote user | 1 | Josh
33 | As a reader, I want to read with a connected reader using audio, so that we can read together | Write source code for connecting with audio | 0.5 | Josh
|  | Review source code for connecting with audio | 0.5 | Alexa
|  | Write unit tests for connecting with audio | 16 | Josh | The estimate for writing the unit tests for "connecting with audio" is estimated at 16 hours, yet writing the source code for this feature is only 0.5 hours. Is either one of these an error? Is the estimate for writing the code underestimated and is the estimate for writing the unit tests overestimated?
|  | Write acceptance criteria for connecting with audio | 1 | Alexa
|  | Write acceptance tests for connecting with audio | 2 | Alexa
|  | Execute acceptance tests for connecting with audio | 0.5 | You
|  | Write internal documentation for connecting with audio | 1 | Kat
|  | Write user manual for connecting with audio | 1 | Kat
|  | TOTAL HOURS | 116.75
|  |  | DEVELOPER | AVAILABLE HOURS | HOURS ASSIGNED
|  |  | Alexa | 35 | 34.5
|  |  | Josh | 40 | 39
|  |  | Kat | 40 | 35.25
|  |  | Your Tasks | - | 8 | The chart at the bottom lists the available hours for each team member. The available hours for the PM need to be added (and should be >= 8).